**Project Status Report III**

|  |
| --- |
| Date of Report Issue/Prepared: March 18, 2020 |

Report Prepared By: Akwasi Himah, Alan Pintor, Elder Guerra, Robert Slezak

Employer/Organization: N/A

|  |  |  |
| --- | --- | --- |
| Project Name:  Project Team:  Period Reporting:  Overall Project Health | Running Champions | |
| T06 | |
| Start Date: March 2**, 2020** | End Date: March 15**, 2020** |
| Yellow (Warning) | |

Summary

|  |
| --- |
| **Project Status Summary** |
| * All pages UI have been developed * Navigation between pages is complete. * Local database is setup and functional. * Remote database is setup and functional. * Tracking page is tracking movement and saving information to database. * Users can Register and data is saved in remote database. * Users can Login after they have Registered. * Users can Logout after Logging in. * Certain Main Menu features are disabled when a user is not logged in. * When Logged in all features are enabled. * Users can create competitions. * Users creating teams only partially complete. |

|  |  |
| --- | --- |
| **Accomplishments As Planned** | **Planned but not Accomplished** |
| Remote database setup complete | Implementing statistics tracking |
| Implemented Registration to remote  database | Implementing team creation and inviting |
| Implemented Login using Registration  information and enabling/disabling features  based on logged in status |  |
| Implementation for creating Competitions  complete |  |

Upcoming Objectives for March 16, 2020, 2020 to March 27, 2020

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | | **Planned Activities/Tasks for Next Period** | |  |
| Activity/Task | Assigned To | | Duration | Date |
| Implement statistics tracking | Akwasi Himah | | 8 days | Mar 20 2020  to  Mar 27 2020 |
| Complete team creation and inviting | Robert Slezak | | 5 days | Mar 18 2020  to  Mar 22 2020 |
| Implement Teams joining Competitions | Robert Slezak | | 5 days | Mar 23 2020  to  Mar 27 2020 |
| Evaluate between payment options (PayPal vs Stripe) | Akwasi Himah | | 2 days | Mar 18 2020  to  Mar 20 2020 |
| Integrate payment into the joining competition process | Alan Pintor | | 8 days | Mar 20 2020  to  Mar 27 2020 |
| Implement logic for competitions starting and finishing (such as winning payment reward) | Elder Guerra | | 6 days | Mar 18 2020  to  Mar 23 2020 |
| Implement user settings (Dark Mode, Distance Units) | Elder Guerra | | 4 days | Mar 24 2020  to  Mar 27 2020 |

|  |  |  |  |
| --- | --- | --- | --- |
|  | **Milestones for Next Period** | | |
| Milestone (Objective) | | Assigned To | Delivery Date |
| Teams (Create, Invite, Join Competitions) | | Robert Slezak | Mar 27 2020 |
| Payment System | | Akwasi Himah,  Alan Pintor | Mar 27 2020 |
| Statistics | | Akwasi Himah | Mar 27 2020 |
| Competition Logic | | Elder Guerra | Mar 27 2020 |
| User Settings | | Elder Guerra | Mar 27 2020 |

Managing Issues and Risk

|  |  |  |
| --- | --- | --- |
| **Issues/Problems** | **Resolution Strategy** | **Due Date** |
| Having time to complete assigned tasks and keep up with other school assignments | We are going to work hard and be there for each other if we need help | Mar 27, 2020 |
| Due to corona virus, being unable to meet in person | Continue to keep in contact online and discuss development progress and issues as necessary | Mar 27, 2020 |

|  |  |  |  |
| --- | --- | --- | --- |
| **Upcoming Risks** | **Risk Ranking**  **(Hi, Med, Low)** | **Risk Impact**  **(Hi, Med, Low)** | **Mitigation Strategy** |
| Time management due to upcoming school assignments | Med | Med | Work hard and be there to help each other |
| Exposure to corona virus may lead to group members being sick and unable to complete their tasks on time | Low | High | Group members are in self-isolation to reduce risk of exposure to the virus |

**NOTE: Attach additional sheets if insufficient space available**

**Submission Guidelines:**

Please submit as “T<team number>\_ProjectStatusReport3”.

For e.g. T36\_ProjectStatusReport3

This is a group submission i.e. one per group.

**Due Dates:**

**Wednesday, March 18, 2020 (11:59 p.m.)**